Terms of Reference (TOR) for Consulting Services on

Detailed Engineering Design for Educational Facility Renovations

- General Information

The joint IsDB/ISFD/GPE "SMART-ED" Project aims to improve access to and the quality of inclusive learning opportunities for all children in the Kyrgyz Republic. The project is implemented by the Ministry of Education (MoE) with funding from the Islamic Development Bank (IsDB), the Islamic Solidarity Fund for Development (ISFD), and the Global Partnership for Education (GPE). This large-scale initiative comprises various components, one of which involves the construction and rehabilitation of educational infrastructure that meets the criteria of inclusive, sustainable, and climate-resilient design.

- Objective

The primary objective of the Consultant's services for Detailed Design Development and Construction Supervision is to provide comprehensive technical services throughout the entire lifecycle of the educational infrastructure improvement component – from design to supervision of construction/rehabilitation works. These services aim to deliver educational facilities that comply with international standards, IsDB guidelines, and national regulatory requirements, while promoting inclusivity, accessibility, energy efficiency, and disaster resilience.

- Project Implementation Sites

The assignment covers 32 facilities. The 32 project sites are distributed across 6 regions as follows:

Chui Region – 6 sites;

Osh Region – 12 sites;

Issyk-Kul Region – 7 sites;

Talas Region – 2 sites;

Jalal-Abad Region – 3 sites;

Batken Region – 2 sites.

Note: The complete list of facilities with their names, locations, and preliminary scope of works is provided in Appendix 1 "List of Facilities". The scope of works for each site is based on the list provided by the MoE. The Consultant shall verify the existing conditions during the site surveys and, if necessary, propose adjustments to the designs and BoQ for approval by the MoE and IsDB.

The assignment comprises three types of service packages (for details, see Appendix 1 "List of Facilities"):

- Type 1 – New construction of 2 facilities;

- Type 2 – Major overhaul / Capital repair of 5 facilities;

- Type 3 – Repair / Refurbishment works in 25 facilities.

- Scope of Services

The Consultant shall provide comprehensive services for the educational infrastructure component, covering the entire project cycle from site preparation through to the end of the warranty period.

Type 1 – New Construction of 2 Facilities:

### 4.1.  Design Preparation and Site Surveys

- Conducting preliminary site visits and surveys for each educational institution (2 sites) to verify existing conditions.

- Conducting topographic surveys and geotechnical investigations.

- Assessing access roads, availability of utilities (water, electricity, sanitation), and any constraints.

- Preparing site survey reports with recommendations for the design.

  - Detailed Design of 2 Facilities and Assistance in Obtaining State Expert Review (SER) Approval

Preparation of detailed architectural, structural, and MEP (HVAC, electrical, plumbing, and sanitation) designs in compliance with the building codes of the Kyrgyz Republic, principles of inclusive and accessible design, as well as best practices in climate resilience and energy efficiency. Furthermore, the Consultant shall develop the Detailed Design Documentation for all disciplines required to pass the State Expert Review and for subsequent tender/construction, including (as applicable):

- Site Plan / External Networks / Site Development (access roads, drainage, site lighting, fencing, accessible routes for persons with reduced mobility (PRM), play/sports grounds if applicable);

- AR (Architectural Design: architectural solutions, layouts, finishes, doors/windows, safety);

- Structural Design (RC/Steel): structural solutions, reinforcement, seismic resilience;

- HVAC (Heating, Ventilation, Air Conditioning: heating, ventilation, and air conditioning if required);

- Plumbing and Drainage (P&D), including sanitary facilities and accessible PRM toilets;

- Electrical (Power & Lighting): power supply, interior/exterior lighting, grounding, lightning protection);

- Telecom / Low-Current Systems (local network/structured cabling, CCTV/Security systems if required, public address systems, internet connectivity as per MoE's specifications);

- Fire Safety / Fire Protection Systems (if required and per expert review requirements: fire alarm/voice alarm systems, etc.);

- Energy Efficiency / Thermal Envelope (thermal performance calculations for building envelope, junction details, elimination of thermal bridges, measures to reduce heat loss);

- Accessibility (Inclusivity) for persons with disabilities and other PRM (entrance, circulation paths, sanitary facilities, wayfinding, safety features);

- Cost Estimate Documentation and BoQ in a tender-ready format suitable for procurement of works;

- Integration of Sustainable Development elements as required by the Project Development Objective, including enhanced thermal insulation, natural daylighting, energy-efficient lighting, readiness for solar energy use, and water-saving systems;

- Development of complete Technical Specifications, Bills of Quantities (BoQ), Cost Estimates, and Construction Schedules;

- Preparation and compilation of all design documentation in compliance with requirements, and facilitation of the State Expert Review process; provision of full technical support to the MoE during the approval process, including responding to comments and making revisions until final approval is obtained;

- Ensuring all design packages are tender-ready after approval.

  - Educational Equipment and Furnishing Fit-Out

- Development, in coordination with the MoE, of detailed technical specifications, room/classroom layout plans, and installation requirements for furniture, educational, and other necessary equipment in accordance with the principles of inclusive, seismic-resilient, and climate-smart design.

- Preparation of a complete list of the aforementioned equipment and furniture compliant with IsDB requirements for inclusion in the tender documentation.

- Supervision of the installation and commissioning of all equipment, ensuring full compliance with approved specifications and contractual requirements.

- Certification of the completion of equipment installation and commissioning, and preparation of a handover report for the MoE.

Type 2 – Major Overhaul / Comprehensive Rehabilitation of 5 Facilities

  - Detailed Design of 5 Facilities

- Development of Detailed Design and Cost Estimate Documentation for the major overhaul of 5 educational institutions (see Appendix 1 "List of Facilities") based on compiled and approved defect reports, in accordance with current construction, technological, fire safety, and sanitary codes, in the manner established by the regulatory legal acts of the Ministry of Construction, Architecture, and Housing and Communal Services of the Kyrgyz Republic. The Detailed Design Documentation must include a "Design Report" and "Architectural, Structural, and Layout Solutions (specifying the types of materials used, patterns, dimensions, and cross-sections)", namely:

- Building Condition Survey Report: specifying the condition of buildings and structures (floor, openings, roof, etc.), external and internal finishes, condition of utility networks (plumbing, HVAC, electrical networks and fixtures, availability of structured cabling networks (internet), video surveillance systems, etc.).

  - As-built survey drawing (with utility network mapping);

  - Demolition plan for openings, floors, roof, etc. and utility networks (with dimensions);

  - Installation plan for openings, floors, roof, etc. and utility networks (with dimensions);

  - External and internal finishing plan (with scope of works);

  - Floor plan (with dimensions);

  - Ceiling plan (with specifications of material types, dimensions, and sections);

  - Lighting plan (interior and exterior, including grounding);

  - Water supply and sewerage system plan;

  - Heating and ventilation system plan;

  - Environmental protection plan;

  - Fire safety system plan;

  - Video surveillance system, structured cabling network;

  - Site development (pedestrian and vehicular access roads, fencing, etc.);

  - Local cost estimates.

- The project design must reflect responsible organization of waste collection and disposal and other environmental standards, as well as comply with social and gender equity (including ramps for persons with disabilities; safe and separate toilets for girls and boys);

- The project design must reflect the provision of computer labs, classrooms and laboratories, workshops, gyms, dining areas, restrooms, and so on.

- Internal utility networks must account for the intended load and comply with the required capacity.

- The number of rooms, room types, quantity of computer equipment, number of classrooms, and other requirements will be preliminarily defined by the Client for design purposes.

- Develop a Bill of Quantities (BoQ) for the preparation of tender documents, within the allocated budget for each educational institution.

- Should any necessary additional works and materials be identified during construction, review and coordinate proposals from contractors for changes to the construction/repair works (BoQ) to ensure compliance with current construction, technological, fire safety, and sanitary codes in the manner established by the regulatory acts of the Ministry of Construction of the Kyrgyz Republic.

- Preparation and compilation of all design documentation in accordance with requirements and obtaining all necessary permits.

- Ensuring all design packages are tender-ready after approval.

  - Educational Equipment and Furnishing Fit-Out

- Development, in coordination with the Ministry of Education of the Kyrgyz Republic (MoE), of detailed technical specifications, room/classroom layout plans, and installation requirements for furniture, educational, and other necessary equipment in accordance with the principles of inclusive, seismic-resilient, and climate-smart design.

- Preparation of a complete list of the aforementioned equipment and furniture compliant with the Islamic Development Bank (IsDB) requirements for inclusion in the tender documentation.

- Supervision of the installation and commissioning of all equipment, ensuring full compliance with the approved specifications and contractual requirements.

- Certification of the completion of equipment installation and commissioning, and preparation of a handover report for the MoE.

Type 3 – Repair / Refurbishment Works in 25 Preschool Educational Institutions

  - Repair Design - Core Components

This assignment covers partial refurbishment of temporary care preschool educational institutions, focusing on priority areas (sanitary facilities, playroom).

- Site inspection and assessment to determine:

  - Defects, damages, malfunctions, and other issues hindering the normal operation of the building;

  - The feasibility of operating the facility under required future conditions;

  - The scope of works (Bill of Quantities) for the repair and restoration works.

- Design Report;

- Site Plan;

- Architectural Design Solutions;

- Determination of the scope of works for cosmetic and routine maintenance of the building premises (prepare a schedule of finishes for interior spaces and facade);

- Inventory data on the building's engineering equipment and networks, summary of engineering solutions (to be filled out separately for water supply and drainage systems, electrical supply, and other types of utility networks);

- List of measures to ensure fire safety during works and environmental protection;

- Cost estimate for the repair and restoration works;

- Other sections, depending on the type of facility and the scope of upcoming works.

  - Educational Equipment and Furnishing Fit-Out

- Development, in coordination with the Ministry of Education of the Kyrgyz Republic (MoE), of detailed technical specifications and room layout plans for priority placement of furniture, educational, and other necessary equipment in accordance with the principles of inclusive, seismic-resilient, and climate-smart design.

- Preparation of a complete list of the aforementioned equipment and furniture compliant with the Islamic Development Bank (IsDB) requirements for inclusion in the tender documentation.

- Supervision of the installation and commissioning of all equipment, ensuring full compliance with the approved specifications and contractual requirements.

- Certification of the completion of equipment installation and commissioning, and preparation of a handover report for the MoE.

- Construction Supervision and Contract Management

- Supervision of all construction/rehabilitation works to ensure compliance with the approved designs, specifications, quality standards, and contract terms.

- Review and approval of the Contractor's shop drawings, submitted materials, work methods, and test reports.

- Monitoring works against the approved construction schedule, identifying deviations, and recommending corrective measures.

- Maintaining a work volume inspection log against the BoQ and a payment tracking register linked to certified works; preparation of a monthly progress report on physical and financial indicators.

- Monitoring compliance with environmental, health, safety, and social safeguards on-site.

- Coordination with the MoE, IsDB, contractors, and relevant local authorities for the seamless implementation of construction/rehabilitation works.

- Maintaining up-to-date contract records, tracking physical and financial progress, and managing variations in accordance with IsDB procedures.

- Supervision During the Defects Liability Period

- Conducting periodic inspections (at least once per quarter) during the 12-month Warranty Period / Defects Liability Period after the issuance of the Taking-Over Certificate for each site.

- Certification of the completion of all remedial works identified during the inspections.

- Preparation of a report upon the completion of the Warranty Period and recommendation for the issuance of the Final Acceptance Certificate.

- Compliance with Applicable Norms and Regulations of the Kyrgyz Republic

### The development of Detailed Design Documentation (DDD), completion of expert reviews and approvals (as required), and subsequent construction supervision shall be carried out in strict compliance with the current regulatory legal acts and normative-technical documents of the Kyrgyz Republic (in the version in force at the date of DDD development), including but not limited to:

- Regulation on the Procedure for Issuing Permits for Design, Construction, Re-profiling, Re-equipment, and Other Modifications of Real Estate Objects and the Procedure for Acceptance of Completed Construction (Repair/Restoration) Objects into Operation in the Kyrgyz Republic, approved by Government Decree No. 12 dated January 17, 2020.

- Construction Rules of the Kyrgyz Republic (SP KR) 13-02:2020 "Re-profiling, Re-planning, and Reconstruction of Buildings in the Existing Development" (and other applicable SP/SR KR concerning major overhaul/reconstruction).

### Architectural-Planning Solutions and Functional Requirements (Education Facilities)

- Construction Norms of the Kyrgyz Republic (SN KR) 31-08:2024 "School Buildings. Design Standards" regarding requirements for layout, safety, evacuation routes, functional zones, etc. (to the extent applicable to the project facilities).

- SN KR 31-04:2018 "Public Buildings and Structures" to the extent applicable to educational/public buildings.

### Seismic Resilience and Structural Safety

- SN KR 20-02:2024 "Earthquake-Resistant Construction. Design Standards" (including provisions for strengthening/restoration/reconstruction in seismic areas).

### Fire Safety

- SN KR 21-01:2018 "Fire Safety of Buildings and Structures" and other applicable KR norms/rules on fire safety (including requirements for alarm/evacuation systems/fire protection/fire alarm systems, as applicable).

### Heating, Ventilation, Air Conditioning, Microclimate

- SN KR 41-04:2022 "Heating, Ventilation, and Air Conditioning" for the design/selection of HVAC solutions and air exchange calculations.

- Applicable sanitary-epidemiological rules and hygienic standards of the Kyrgyz Republic for educational institutions, regarding microclimate, ventilation, lighting, sanitary facilities, drinking water supply, etc.

### Accessibility for Persons with Disabilities and Other Persons with Reduced Mobility (PRM) - Inclusive Environment

- SN KR 35-01:2018 "Design of Living Environment Considering the Needs of Persons with Disabilities";

- SP KR 35-101:2018 "Ensuring Accessibility of Living Environment in Planning Solutions of Buildings for Persons with Disabilities".

### Thermal Protection, Energy Efficiency, Lighting

- KR normative standards on thermal protection of buildings and construction climatology (in the current version), as well as norms for natural and artificial lighting, for the selection of building envelope structures, windows/doors, calculation of heat losses, and illumination levels.

### In the absence of a direct KR norm on specific specialized issues, the application of interstate standards/GOST and other norms applicable in the territory of the Kyrgyz Republic is permitted, provided they do not contradict the mandatory requirements of the KR and the proposed solutions are coordinated through established procedures.

- Reporting Requirements

The Consultant shall prepare and submit the following reports in English and Russian:

- Inception Report (first month): methodology, work plan, staffing plan, mobilization schedule.

- Design Stage Deliverables: survey reports, geotechnical reports, detailed designs, specifications, Bills of Quantities (BoQ), cost estimates, documentation package for State Expert Review, tender documents.

- Monthly Construction Supervision Reports: site progress, quality assurance, compliance with safeguards, updated construction schedules, as well as status of procurement, delivery, and installation of equipment.

- Contract Management Reports: financial status, variation justifications, payment schedules, BoQ verification summary, and payment tracking dashboard.

- Final Completion Report: prepared in accordance with the standard framework and templates of the IsDB for completion reports, summarizing the entire assignment, achievement of outcomes/indicators, procurement and contract management, physical and financial progress and payments, safeguards compliance, completion of the Warranty Period, lessons learned, and recommendations.

- Contract Type and Structure

## The Consultant and the Client (MoE) shall sign a single contract consisting of two independent parts:

## 1) Part A: Development of Detailed Design Documentation and Procurement Support

- Contract Type: Fixed-Price Contract (Lump Sum).

- Payments are made upon acceptance of approved deliverables and signing of Certificates of Work Completion in accordance with the Payment Schedule for Part A.

## 2) Part B: Construction Supervision and Contract Management

- Contract Type: Time-Based Contract with a Ceiling Amount.

- Payments are made monthly based on approved reports and supervision timesheets/logs confirming actual qualified time expended. Reimbursement of agreed travel and other reimbursable expenses is made based on supporting documents.

## Parts A and B are independent in terms of their scope and payment. The commencement of Part B shall occur after the award of construction contracts and/or upon written instruction from the Client to initiate supervision for the respective facilities.

- Project Schedule

The overall duration of services is expected to be approximately 48 months from the Consultant's mobilization until the completion of the Warranty Period for all sites. An indicative schedule is as follows:

Part A (Lump Sum): Detailed Design and Procurement Support

- Detailed Design Development, preparation of Detailed Design Documentation, and facilitation of State Expert Review (as required): approximately 6 months. Includes site surveys, investigations, design development, technical specifications, cost estimates, revisions based on comments, and support until obtaining necessary approvals/conclusions (as applicable).

- Procurement Support (for construction works and/or equipment, as required): approximately 4-6 months. Includes preparation of tender documents, responding to bidders' queries, participation in clarifications, assistance in bid evaluation, and preparation of contract award documentation. This phase may partially overlap with the final stages of design.

Part B (Time-Based): Construction Supervision and Contract Management

- Construction Supervision and Contract Management: approximately 30–36 months. Includes regular on-site supervision, contract administration, quality control, monitoring of labor/environmental/fire safety compliance, and progress reporting for 32 sites. The actual duration depends on the number of sites implemented in parallel, procurement schedules, and the pace of contractors' work.

- Supervision During the Warranty Period: 12 months. Includes post-construction inspections, monitoring of defect rectification, and preparation of recommendations for final acceptance.

The schedule may be adjusted depending on procurement timelines, contractor performance, site conditions, and other project requirements.

11. Payments

### 11.1. Development of Detailed Design Documentation and Procurement Support (Lump Sum)

Payments under Part A shall be made in stages based on Certificates of Services Rendered (CSR) signed by both parties and the Client's approval of the relevant stage deliverables. The period for the Client's review and acceptance of deliverables shall be up to 10 working days for Stage 1 and up to 20 working days for Stages 2-4.

| Reports | Payments |
| --- | --- |
| Stage 1. Inception Report: Building Surveys and Preparation of Defect Reports for All Educational Institutions, Including Photographic Documentation and Recommendations, within 30 calendar days from the contract signing date. | Advance payment of 10% of the value of Part A within 10 working days after the Client's approval of the defect reports for all facilities. |
| Stage 2. Submission of a Complete Set of Detailed Design Documentation (DDD) for the Repair/Rehabilitation of Kindergartens (25 facilities), including drawings, specifications, and cost estimates (3 hard copies and an electronic copy), within 60 calendar days after the Client's approval of the Stage 1 results. | 20% of the value of Part A within 20 working days after acceptance of the complete DDD package for 25 facilities. |
| Stage 3. Submission of a Complete Set of Detailed Design Documentation (DDD) for the Repair/Rehabilitation of 5 Educational Institutions, including drawings, specifications, and cost estimates (3 hard copies and an electronic copy), within 120 calendar days after the Client's approval of the Stage 1 results. | 30% of the value of Part A within 20 working days after acceptance of the complete DDD package for 5 facilities. |
| Stage 4. Submission of a Complete Set of Detailed Design Documentation (DDD) for the Construction of 2 Educational Institutions, including drawings, specifications, and cost estimates (3 hard copies and an electronic copy), within 180 calendar days after the Client's approval of the Stage 1 results. | 35% of the value of Part A within 20 working days after acceptance of the complete DDD package for 2 facilities. |
| Stage 5. Incorporation of Changes/Revisions into the Detailed Design Documentation (DDD) During Implementation (including those based on comments from the MoE/IsDB/State Expert Review, as well as approved change requests during the construction period), including updates to cost estimates as necessary. | 5% of the value of Part A upon completion of all construction works by the contractors and acceptance by the Client of the final package of revisions/changes. |

### Phased acceptance of DDD packages for groups of facilities is permitted in cases of readiness on a per-facility basis, while maintaining the overall percentage distribution of payments by stage.

### 11.2. Part B: Construction Supervision and Contract Management (Time-Based)

## Payment under Part B shall be made monthly based on the actual time worked, supported by approved reports and supervision logs/timesheets. Travel expenses and other agreed-upon reimbursable costs shall be compensated based on supporting documents and in accordance with the contract terms.

## 12. Qualification Requirements

Interested consulting firms must demonstrate the technical capacity, relevant industry experience, and adequate staffing to deliver services across multiple, geographically dispersed school sites. The firm shall provide:

  - Relevant Project Experience

### The company must possess proven experience in the design of major overhaul or new construction of buildings. As proof, it shall provide copies of 2 (two) similar contracts successfully completed within the last 5 (five) years, along with supporting documents confirming the completion of works (acceptance certificates), as well as 2 (two) reference letters from clients for these projects.

### Please be advised that the possession of a Design and Estimate Documentation Development License of at least Category II (Second Level), valid in the Kyrgyz Republic, will be an additional requirement for contract award.

  - Experience in Implementing Donor-Funded Projects

### The company must have confirmed experience working under contracts financed by international financial institutions such as IsDB, WB, ADB, or other multilateral development banks. For verification, a copy of 1 (one) such contract, completed within the last 5 (five) years, must be provided along with supporting documents confirming the completion of works (acceptance certificates).

  - Key Personnel Qualifications

### The company must demonstrate the ability to assemble a qualified multi-disciplinary team sufficient to perform the full range of services: from design and procurement support to construction supervision, contract management, and warranty period monitoring across multiple sites. In confirmation, it shall provide curricula vitae (CVs) and relevant certificates for all key specialists to be engaged in the project.

### 13. Team Composition

The Consultant shall mobilize a qualified multi-disciplinary team adequate to the scale, complexity, and geographical dispersion of the assignment (32 sites across several regions). The team must have sufficient capacity to supervise multiple sites in parallel and ensure regular presence at all active sites.

Minimum Composition of Key Experts:

1. Team Leader / Chief Construction Engineer – 1 position

- Master's degree in civil engineering, architecture, or construction management.

- Minimum 7 years of relevant experience managing similar donor-funded design and supervision contracts.

2. Architect – 1 position

- Degree in architecture.

- Minimum 7 years of experience in the design of public buildings or schools.

3. Civil/Structural Engineers – 3 positions

- Degree in civil or structural engineering.

- Minimum 5 years of experience in design and supervision, including compliance with seismic safety requirements per Kyrgyz standards.

4. Mechanical Engineer – 1 position

- Degree in mechanical engineering.

- Minimum 5 years of experience in the design and supervision of HVAC, plumbing, and sanitation systems.

5. Electrical Engineer – 1 position

- Degree in electrical engineering.

- Minimum 5 years of experience in designing electrical systems, including lighting, power distribution, and readiness for renewable/solar energy sources.

6. Quantity Surveyor / Cost Estimation Specialist – 1 position

- Degree in quantity surveying, civil engineering, or equivalent.

- Minimum 5 years of experience in preparing BoQs, cost estimation, and verification of works during construction.

7. Procurement Specialist – 1 position

- Degree in procurement, engineering, or a related field.

- Minimum 5 years of experience in preparing tender documents, bid evaluation, and procurement of works for donor-funded projects.

8. Environmental Specialist – 1 position

- Degree in environmental sciences or a related field.

- Minimum 5 years of experience in environmental safeguards for construction projects.

9. Social Safeguards Specialist – 1 position

- Degree in social sciences or a related field.

- Minimum 5 years of experience in social impact assessment and community engagement in infrastructure projects.

10. Health and Safety Specialist – 1 position

- Degree in occupational health and safety, civil engineering, or a related field.

- Minimum 5 years of experience in managing health and safety on construction sites.

Minimum Site Supervision Staff:

- Regional Supervision Engineers – no fewer than 8 positions (distributed across geographical clusters to ensure adequate coverage; Chui and Osh regions may require more than one engineer due to the large number of sites), responsible for daily monitoring of works within their assigned cluster.

- Assistant Engineers / Site Inspectors – no fewer than 8 positions, assigned to clusters with multiple active sites in parallel to support Regional Engineers and ensure full coverage.

Support Staff (as required):

This may include CAD operators/draftsmen, surveyors, administrative and logistics personnel, as well as one Equipment/ICT Specialist to support the design, procurement, and installation of equipment.

Bidders may propose additional personnel if they deem it necessary for the timely and high-quality execution of the works. Proposals with an enhanced staffing plan will be viewed favorably, provided it is duly justified.

### 14. Selection Method

The Consultant will be selected using the Least-Cost Selection (LCS) method among qualified national consulting firms in accordance with the IsDB Procurement Guidelines. A shortlist of eligible firms will be invited to submit technical and financial proposals. Only firms achieving the minimum technical score will be considered for financial evaluation. The contract will be awarded to the firm with the lowest evaluated financial bid among those passing the technical threshold.

Appendix 1 "List of Facilities"

| No. | Facility Name | Address | No. of Student Places | Type of Required Construction Works |
| --- | --- | --- | --- | --- |
| Works Type #1 (2 facilities) |  |  |  |  |
| 1 | Issyk-Kul Regional Institute of Education | Karakol city | 250 | New construction |
| 2 | Osh Regional Institute of Education | Osh city | 250 | New construction |
| Works Type #2 (5 facilities) |  |  |  |  |
| 3 | "Manas" Boarding School | Talas Region, Bakai-Ata District, Kyzyl-Sai village, Kochorkul-Ata St., 63 | 320 | Major renovation / construction |
| 4 | Zh.Mavlyanov Gymnasium-Boarding School | Jalal-Abad Region, Aksy District, Kerben city, Umetaliev St. | 1007 | Major renovation / construction |
| 5 | N.Isanov Gymnasium-Boarding School | Jalal-Abad Region, Nooken District, Kochkor-Ata city, Mutsrazhan St., 1 | 887 | Major renovation / construction |
| 6 | Batken Regional Boarding School | Batken Region, Batken city, Sabirov St., 1. | 717 | Major renovation / construction |
| 7 | Kadyrmamat uulu Abdyrazak Lyceum-Boarding School | Osh Region, Alay District, Gulcho village, Kadyrov St., 10 | 300 | Major renovation / construction |
| Works Type #3 (25 facilities) |  |  |  |  |
| 8 | Municipal Budgetary Institution (MBI) (former kindergarten) | Chui Region, Ysyk-Ata District, Uzun-Kyr village, Novo-Pokrovka rural area, Lenin St., 479 | 50 | Repair |
| 9 | Kindergarten "MIS" | Chui Region, Kant city, Tagaev St., 3 | 400 | Repair |
| 10 | "Vasilyok" (former building) | Chui Region, Kant city, Luxemburg village, Stroitelnaya St., 3 | 250 | Repair |
| 11 | MBI | Chui Region, Alamudun District, S.Chokmorov rural municipality, Oktyabr village, Partsyezd St., 22 | 180 | Repair |
| 12 | MBI | Chui Region, Alamudun District, S.Chokmorov rural municipality, Oktyabr village, Gogol St. | 150 | Repair |
| 13 | MBI | Chui Region, Panfilov District, Kuramin rural municipality, Panfilov village, Tsentralnaya St., 281 | 180 | Repair |
| 14 | Former building of the ayil okmotu (local administration) | Osh Region, Uzgen District, Altyn-Bulak ayil okmotu, Kara-Shoro village, Shamal-Terek village | 30 | Repair |
| 15 | Former building of the ayil okmotu (local administration) | Osh Region, Uzgen District, Zhazy ayil okmotu, Kayrat village | 75 | Repair |
| 16 | Former cadastre building | Osh Region, Aravan District, S.Yusupova ayil okmotu, Aravan village, Kh. Abdullaev St. | 150 | Repair |
| 17 | Former dormitory of the Too-Moyun Gymnasium | Osh Region, Aravan District, Too-Moyun ayil okmotu, Ak-Shar village | 100 | Repair |
| 18 | Former office building | Osh Region, Aravan District, Too-Moyun ayil okmotu, Nayman village | 75 | Repair |
| 19 | Vacant kindergarten building | Osh Region, Aravan District, Too-Moyun ayil okmotu, Aviz village | 120 | Repair |
| 20 | Former building of Secondary School No. 64 named after T. Shamyrbek uulu | Osh Region, Kara-Suu District, Bash-Bulak ayil okmotu, Achy village | 100 | Repair |
| 21 | Former building of Secondary School No. 121 named after Zh.Sheriev | Osh Region, Kara-Suu District, Papan ayil okmotu, Andagul village | 100 | Repair |
| 22 | Former building of Secondary School No. 63 named after the 70th Anniversary of October | Osh Region, Kara-Suu District, Otuz-Adyr ayil okmotu, Zhany Kyzyl-Suu village | 90 | Repair |
| 23 | Ayil okmotu (local administration) building | Talas Region, Talas District, Besh-Tash rural municipality, A. Ogonbaeva village | 75 | Repair |
| 24 | Old building of School No. 11 named after Teshebaev | Jalal-Abad Region, Toktogul city, Aral village | 70 | Repair |
| 25 | ZhBBM building named after Zh.Chabaldaev | Issyk-Kul Region, Jeti-Oguz District, Saruu village | 120 | Repair |
| 26 | Kindergarten "Solnyshko" | Issyk-Kul Region, Jeti-Oguz District, Kyzyl-Suu village | 240 | Repair |
| 27 | Returned building | Issyk-Kul Region, Svetlaya Polyana village, Barakanov St., a-6 | 100 | Repair |
| 28 | Former school building in Kosh-Dyobo village | Issyk-Kul Region, Tyup District, Karasaev rural municipality, Yntymak village | 100 | Repair |
| 29 | Old school building named after A.Kolbaev | Issyk-Kul Region, Ton District, Bolot Mambetov ayil okmotu, Jer-Ui village | 100 | Repair |
| 30 | Old building of Secondary School named after Zh.Shabirov | Issyk-Kul Region, Issyk-Kul District, Zhusup Abdrakhmanov rural municipality, Orto-Oruktu village | 50 | Repair |
| 31 | Former building of Preschool Institution No. 12 "Ak-Kuu" | Batken Region, Kyzyl-Kya city, Zhusubaliev St., 127 | 120 | Repair |
| 32 | Kindergarten No. 34 | Osh city, A.Masaliev St., No. 25 | not specified | Repair |